## Sheet1
Group | Subgroup | quarter commencing | 2019-07-01 | 2019-10-01 | 2020-01-01 | 2020-04-01 | 2020-07-01 | 2020-10-01 | 2021-01-01 | 2021-04-01 | 2021-07-01 | 2021-10-01 | 2022-01-01 | 2022-04-01 | 2022-07-01 | 2022-10-01 | 2023-01-01 | 2023-04-01 | 2023-07-01 | 2023-10-01 | 2024-01-01 | 2024-04-01 | 2024-07-01 | 2024-10-01 | 2025-01-01 | 2025-04-01 | 2025-07-01 | 2025-10-01
A | 0 | Ofgem Policy decisions
A | 1 | Decision on MHHS
A | 2
A | 3
A | 4
A | 5
A | 6
A | 7
A | 8
A | 9
A | 10
B | 0 | Governance
B | 1
B | 2
B | 3
B | 4
B | 5
B | 6
B | 7
B | 8
B | 9
B | 10
C | 0 | Central Systems | bar: 2020-04-01 to 2024-04-01
C | 1 | Consider architectural solutions
C | 2 | Governance changes
C | 3 | Design & build system changes
C | 4 | test
C | 5 | Implement | bar: 2023-04-01
C | 6 | Migration
C | 7
C | 8
C | 9
C | 10
D | 0 | Registration | bar: 2020-10-01 to 2022-07-01; 2024-07-01
D | 1 | Faster switching changes complete
D | 2 | Develop requirements
D | 3 | Governance changes
D | 4 | Design & build system changes
D | 5 | Test
D | 6 | Implement | bar: 2022-07-01
D | 7 | Remove HHDA/NHHDA functions
E | 0 | Smart Segment | bar: 2020-04-01 to 2022-04-01; 2023-07-01 to 2024-04-01
E | 1 | Change to SEC governance
E | 2 | Change to BSC governance
E | 3 | Implement SEC role
E | 4 | Design & build system changes
E | 5 | Test
E | 6 | Start migration
E | 7
E | 8
E | 9
E | 10
F | 0 | Advanced Segment | bar: 2019-07-01 to 2021-01-01; 2022-04-01 to 2022-10-01; 2023-07-01 to 2023-10-01
F | 1 | Using current framework - Develop initial changes
F | 2 | Governance changes
F | 3 | Complete installation of Advanced Meter (SLC)
F | 4 | Implement all CT metering HH settlement | bar: 2021-01-01
F | 5 | Migrate all to using direct Registration
F | 6 | Migrate data to send to central systems
F | 7
F | 8
F | 9
F | 10
G | 0 | Unmetered Segment | bar: 2019-07-01 to 2021-01-01; 2022-04-01 to 2022-10-01; 2023-07-01 to 2023-10-01
G | 1 | Using current framework - Develop initial changes
G | 2 | Governance changes
G | 3 | Design & build system changes
G | 4 | Test
G | 5 | Implement - all over 100,000kWh EACs, 500 MPANs
G | 6 | Implement - all remaining 30k MPANs | bar: 2021-01-01
G | 7 | Migrate all to using direct Registration
G | 8 | Migrate data to send to central systems
G | 9
G | 10
H | 0 | DUoS
H | 1
H | 2
H | 3
H | 4
H | 5
H | 6
H | 7
H | 8
H | 9
H | 10
I | 0 | Settlement timetable | bar: 2019-10-01 to 2020-07-01
I | 1 | Revise Disputes timetable | bar: 2023-07-01 to 2024-07-01
I | 2 | Governance change
I | 3 | Implement revised Dispute timetable | bar: 2020-07-01
I | 4 | Review settlement timetable
I | 5 | Governance changes
I | 6 | Implement | bar: 2024-07-01
I | 7
I | 8
I | 9
I | 10
J | 0 | Settlement Impact
J | 1 | MPANs in segment settling HH - Smart | 0.2% | 0.2% | 0.2% | 0.2% | 0.2% | 0.2% | 0.2% | 0.2% | 0.2% | 0.2% | 0.2% | 0.2% | 0.2% | 0.2% | 0.2% | 0.2% | 10% | 40% | 80% | 100% | 100%
J | 2 | MPANs in segment settling HH - Advanced | 77% | 80% | 82% | 84% | 86% | 90% | 95% | 96% | 97% | 98% | 99% | 99% | 99% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
J | 3 | MPANs in segment settling HH - Unmetered | 1.2% | 1.2% | 1.2% | 2.4% | 2.4% | 2.4% | 90% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
J | 4 | Energy in segment settling HH - Smart | 0.2% | 0.2% | 0.2% | 0.2% | 0.2% | 0.2% | 0.2% | 0.2% | 0.2% | 0.2% | 0.2% | 0.2% | 0.2% | 0.2% | 0.2% | 0.2% | 10% | 40% | 80% | 100% | 100%
J | 5 | Energy in segment settling HH - Advanced | 90% | 90% | 90% | 90% | 90% | 90% | 95% | 96% | 97% | 98% | 99% | 99% | 99% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
J | 6 | Energy in segment settling HH - Unmetered | 78% | 78% | 78% | 85% | 85% | 85% | 90% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
J | 7 | MWh in segment settling HH - Smart
J | 8 | MWh in segment settling HH - Advanced
J | 9 | MWh in segment settling HH - Unmetered
J | 10