## New Connection
Action: Send D0383
By: LDSO
Recipient: MOA
Timescale: Within 5WD of completion of Commissioning.
Action: Commissioning of Meter and assessment of overall accuracy of Metering System
By: MOA
Recipient: N/A
Timescale: First instance: within 32WD of Energisation
Second instance: within 80 WD of Energisation
Any other instances: Following receipt of D0384
Action: Commissioning of all items of Metering Equipment installed up to and including the testing facilities
By: LDSO
Recipient: NA
Timescale: Within 16WD of Energisation
Decision: Has D0383 been received within 21 WD of Energisation?
Responsible: MOA
Decision: Have all items of Metering Equipment been Commissioned?
Responsible: MOA
Action: Send D0384 (complete)
By: MOA
Recipient: Supplier
Timescale: Within 5 WD of complete Commissioning
Action: Send D0384 (defect/omission)
By: MOA
Recipient: Supplier
Timescale: First instance: 33WD following Energisation
Any other instances: Following attempted Commissioning test
Action: Resolution of defect or creation of action plan for resolution
By: Supplier
Recipient: NA
Timescale: Following receipt of D0384.
Action: Send D0384
By: Supplier
Recipient: MOA
Timescale: First instance: Within 65 WD of Energisation or following completed resolution action
Any other instances: Following completed resolution action
Yes
No
Yes
Action: Send D0384 (defect/omission)
By: MOA
Recipient: Supplier
Timescale: 22WD following Energisation
No